## Gantt Chart Template
GANTT CHART
Task name | Start date | End date | Assigned | Status | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06
PHASE 1: PROJECT INITIATION & ARCHITECTURE SETUP
Task 1.1: IEEE 830 SRS Specification & Architecture | 2026-07-10 | 2026-07-22 | Abhinava K | Done
Task 1.2: Environment Setup (Docker, NestJS & React Native) | 2026-07-20 | 2026-07-27 | Parth P | Done
Task 1.3: Database Layer (PostgreSQL 15, pgvector, Redis) | 2026-07-24 | 2026-07-31 | Jahaan S | Done
PHASE 2: CORE PLATFORM & IDENTITY INFRASTRUCTURE
Task 2.1: Auth Engine (REQ-AUTH: OAuth2, JWT, Argon2id) | 2026-08-01 | 2026-08-10 | Abhinava K | In process
Task 2.2: User Management & Settings (REQ-USER: Profiles, GDPR) | 2026-08-08 | 2026-08-15 | Parth P | In process
Task 2.3: Thin Client Core UI (HomeScreen, ProfileScreen) | 2026-08-12 | 2026-08-21 | Jahaan S | Open
PHASE 3: AI GATEWAY & MULTI-AGENT ENGINE
Task 3.1: NestJS AI Gateway (REQ-AIGW: Intent Classifier & Context) | 2026-08-22 | 2026-09-01 | Abhinava K | Open
Task 3.2: Python CrewAI Integration (FastAPI, Gemini/Groq) | 2026-08-28 | 2026-09-07 | Parth P | Open
Task 3.3: Multimodal AI Screen (AIScreen: Chat, Voice, Vision) | 2026-09-03 | 2026-09-11 | Jahaan S | Open
PHASE 4: CORE DOMAIN SUBSYSTEMS DEVELOPMENT
Task 4.1: Planner Engine (REQ-PLAN: Calendar, Eisenhower, Habits) | 2026-09-12 | 2026-09-21 | Abhinava K | Open
Task 4.2: Notes Vault & Knowledge Base (REQ-NOTE: Markdown, pgvector) | 2026-09-18 | 2026-09-27 | Parth P | Open
Task 4.3: Expense Engine & OCR (REQ-EXP: Vision API Receipts Ledger) | 2026-09-24 | 2026-10-03 | Jahaan S | Open
Task 4.4: Document Vault & Study Hub (REQ-DOC, REQ-STDY: SM-2 Engine) | 2026-09-29 | 2026-10-09 | Parth P | Open
PHASE 5: ADVANCED INTELLIGENCE & THIRD-PARTY SYNC
Task 5.1: Long-Term Memory Engine (REQ-MEM: Memory Vault & Context) | 2026-10-05 | 2026-10-13 | Abhinava K | Open
Task 5.2: Universal Search Engine (REQ-SRCH: RRF Hybrid Vector Search) | 2026-10-10 | 2026-10-18 | Jahaan S | Open
Task 5.3: Google Workspace Sync Engine (REQ-GGL: Calendar, Gmail, Photos) | 2026-10-14 | 2026-10-23 | Parth P | Open
PHASE 6: VERIFICATION, TUNING & FINAL DELIVERY
Task 6.1: End-to-End Integration & Security Audits (NFR Checks) | 2026-10-24 | 2026-10-30 | Abhinava K | Open
Task 6.2: User Acceptance Testing (UAT) & Performance Profiling | 2026-10-28 | 2026-11-03 | Parth P | Open
Task 6.3: Final Production Release & Documentation Handover | 2026-11-01 | 2026-11-06 | Core Team | Open
Insert new rows ABOVE this one